Plan to Create MHU’s Ethics Across the Curriculum Program

From: Elizabeth Whiting Pierce

To: John Omachonu

August 5, 2019

September 2019

- Recruit advisory council. Possible Members: Adkins, Myer, Martin-McCoy, Mathematician, Historian, Two professional school professors, AGS rep.

- With council, review plan to create Ethics Across the Curriculum Map

October 2019

- Meet with Program Coordinators Council to discuss mapping process

- Meet with Deans Council to discuss mapping process

- Implement EAC Mapping

  - Read through course catalog

  - Summarize ethics in every program, using the Harvard’s HULA human development model

  - Ask Program Coordinators to review the summaries I’ve written for their programs and show me what I’ve missed or misunderstood

  - Use that information to create an Ethics Across the Curriculum Map (chart that shows which courses focus on which realms of human development—personal, professional, communal/civic—and the content of that focus)

November 2019

- Present map at faculty forum

- Revise map per feedback from faculty forum

December 2019-May 2020

- Make plans with various MHU stakeholders to use EAC Map in some of the following ways:

  - Identify existing ethical commitments across faculty and curriculum

  - Make decisions about curriculum changes within programs or Gen Ed

  - Target professional development resources for instructors of EAC courses

  - Identify potential community engagement partners for programs and courses

  - Interdisciplinary scholarship on ethics pedagogy

  - Improve appeals to individual donors and foundations

  - Plan linked course activities…trips, especially

  - Consolidate