Mentor/Faculty Fellow training outline

Part A.

Week 1 Sept 21: Orientation for the ACE Framework

Weeks 2-5 Sept 28 – Oct 30: Participate in the 4-week course

a. complete workbook activities and all videos

b. meet with area content person each week

c. create notes of what works and what needs to be shifted to fit with MHU

Paid 1/3 stipend

Part B.

Weeks 6 – 9 Nov. 2-23: Work to collect / develop resources that fit MHU (videos of our own staff and resources) while working with area content person

Week 9-12 Nov 30-Dec 18: Put new content into MHU LMS /Pilot the course with our group before releasing to selected faculty

Paid 1/3 stipend

Part C:

Week 13-16: Jan 4-29 Pilot the course with 10-20 selected faculty as Faculty Fellow Mentors of the ACE Framework

Week 17-18 Evaluations of overall ACE Framework project   
Paid 1/3 stipend